## Sheet1
Issues | Category | Action items
Deadlock issue | Issue to be fixed | DevOps team needs to check
DevOps is down | Need more information | Need more information from Rama
Rule count mismatch error | Need to add an enhancement | Connect with dev team and Rama to understand how frequently we are getting this issue and why are we getting this
Chaos environment we dont have pipelines because of less deployments | Need to add an enhancement | Create CICD pipeline
Access issues to other team members | Training opportunity | Can provide build access to all the team members
Prepare training video
Performance team is not ready for CICD setup | Need more information | Setup a call with PERF team and understand the blockers and needs to work on that