## Work List (hidden)
Goal | Task breakdown | Dependency | Priority | DevSecOps | Monitoring | Owner | Status | Timeline
AWS migration | AWS - e-mail Notification | Need to resolve issues before completing | High | Yes |  | Naveen / Anjali | In Progress
AWS migration | AWS - Non-PROD Pipeline |  | High | Yes |  | Anjali | In Progress |  | Naveen | 8 | Kiran | 8
AWS migration | AWS - Prod Pipeline |  | High | Yes |  | Naveen / Anjali | Not Started |  | AWS - e-mail Notification | 2 | SC 8.4 - SQL Automation | 2
AWS migration | AWS - rollback procedure | DB issue | High | Yes |  | Naveen / Anjali | In Progress |  | KM testing pipeline integration | 2 | ASPEN - Non-PROD Pipeline | 1
AWS migration | AWS - SecOps (Checkmarx) |  | High | Yes |  | Aishwarya | In Progress |  | Follow up | 1 | APSEN - SQL automation | 3
AWS migration | Onboard Aternity |  | High |  | Yes | Epari |  |  | Ad hoc | 1 | Compass 8.4 - Prod Pipeline | 2
AWS migration | Onboard Broadcom |  | High |  | Yes | Sai |  |  | KT | 2
AWS migration | Onboard Splunk |  | High |  | Yes | Lakshmi
AWS migration | Peformance Testing (AppD) |  | High |  | Yes | Sai
Chaos application OCP 4.X pipelines | Aumi-chaos-proxy-pipeline |  | LOW | No | No | New People | Completed |  | Anjali | 4 | Prasanna | 4
Chaos application OCP 4.X pipelines | Gbdcompass-chaos-proxy-pipeline |  | LOW | No | No | New People | Completed |  | DevSecOps (Pega) | 2 | Checkmarx API | 2
Chaos application OCP 4.X pipelines | Gbdcompass-custom-chaos-proxy-pipeline |  | LOW | No | No | New People | Completed |  | Adhoc | 1 | ad hoc | 1
Chaos application OCP 4.X pipelines | Nextgen-chaos-proxy-pipeline |  | LOW | No | No | New People | Completed |  | AWS PERF pega setup and validation | 1 | Compass 8.4 - SQL Automation | 1
Chaos application OCP 4.X pipelines | Sea-chaos-proxy-pipeline |  | LOW | No | No | New People | Completed
Chaos application OCP 4.X Services and routes configuration | Aumi-chaos-proxy-pipeline |  | LOW | No | No | Kiran | Completed
Chaos application OCP 4.X Services and routes configuration | Gbdcompass-chaos-proxy-pipeline |  | LOW | No | No | Srinaveen | Completed |  | Hemant | 8 | Sri | 8
Chaos application OCP 4.X Services and routes configuration | Gbdcompass-custom-chaos-proxy-pipeline |  | LOW | No | No | Aishwarya | Completed |  | adhoc | 2 | Ad hoc | 2
Chaos application OCP 4.X Services and routes configuration | Nextgen-chaos-proxy-pipeline |  | LOW | No | No | Prasanna | Completed |  | Splunk Dashboard (Monitoring Env Health) | 2 | ASPEN - Non-PROD Pipeline | 2
Chaos application OCP 4.X Services and routes configuration | Sea-chaos-proxy-pipeline |  | LOW | No | No | Naveen | Completed |  | Scripting automation | 1 | ASPEN - rollback procedure | 2
Compass 8.4 Upgrade | Compass 8.4 - Non-PROD Pipeline |  | Medium/High | Yes |  | Kiran | Completed |  | SC pipeline logs | 3 | ASPEN - SecOps (Checkmarx) | 2
Compass 8.4 Upgrade | Compass 8.4 - Prod Pipeline |  | Medium/High | Yes |  | Kiran | Not Started
Compass 8.4 Upgrade | Compass 8.4 - rollback procedure |  | Medium/High | Yes |  | Kiran | Completed
Compass 8.4 Upgrade | Compass 8.4 - SecOps (Checkmarx) |  | Medium/High | Yes |  | Kiran | Completed |  |  |  | Aish | 8
Compass 8.4 Upgrade | Compass 8.4 - SQL Automation | Status of Oracle migration to prioritize | Medium/High | Yes |  | Naveen | Not Started |  |  |  |  | 1
Compass 8.4 Upgrade | Update AppDynamics |  | Medium/High |  | Yes | Sai | [5 empty] | 1
Compass 8.4 Upgrade | Update Aternity |  | Medium/High |  | Yes | Epari | [5 empty] | 3
Compass 8.4 Upgrade | Update Splunk |  | Medium/High |  | Yes | Lakshmi | [5 empty] | 1
Compass Oracle Upgrade Support | Update AppDynamics |  | Medium |  | Yes | [6 empty] | 2
Compass Oracle Upgrade Support | Update DevSecOps |  | Medium |  | Yes
Control & Balance | Compass Dashboards |  | High |  | Yes
Control & Balance | Compass Reports |  | High |  | Yes
Control & Balance | Solution Central Dashboards |  | High |  | Yes
Control & Balance | Solution Central Reports |  | High |  | Yes
DBG application OCP 4.X | DBG - e-mail Notification |  | LOW | Yes |  |  | Not Started
DBG application OCP 4.X | DBG - Non-PROD Pipeline |  | LOW | Yes |  |  | Not Started
DBG application OCP 4.X | DBG - Prod Pipeline |  | LOW | Yes |  |  | Not Started
DBG application OCP 4.X | DBG - rollback procedure |  | LOW | Yes |  |  | Not Started
DBG application OCP 4.X | DBG - SecOps (Checkmarx) |  | LOW | Yes |  |  | Not Started
DevOps Enhancements | Add SecOps to DevOps > DevSecOps (Checkmarx) |  | High | Yes |  | Naveen | Complete
DevOps Enhancements | Add SecOps to DevOps > DevSecOps (Pega) |  | High | Yes |  | Anjali | In Progress
DevOps Enhancements | Add SecOps to DevOps > DevSecOps (Prima Cloud) |  | High | Yes |  | Naveen | Not Started
DevOps Enhancements | On-Demand Release | Anthem Release Management Process | Low | Yes
DevOps Enhancements | Performance testing pipelines for all the apps |  | Medium | Yes
DevOps Enhancements | POC for PEGA Deployment Manager |  | Medium | Yes
DevOps Enhancements | Regression testing pipelines for all the apps |  | Medium | Yes
DevOps Enhancements | Smoke testing pipelines for all the apps |  | Medium | Yes
DevOps Enhancements | Splunk Dashboard (Checkmarx) |  | High | Yes | Yes | Hemant | In Progress
DevOps Enhancements | Splunk Dashboard (Monitoring Env Health) |  | High | Yes | Yes | Hemant | In Progress
DevOps Enhancements | UiPath PoV |  | Medium/High | Yes
EagleEye: Maintenance & Upgrade |  |  | Ongoing | Yes | Yes
EagleEye: Reporting |  |  | Ongoing | Yes | Yes
Pega KM | KM - e-mail Notification |  | High | Yes |  | Anjali | Completed
Pega KM | KM - Non-PROD Pipeline |  | High | Yes |  | Naveen | Completed
Pega KM | KM - Prod Pipeline |  | High | Yes |  | Prasanna | In Progress
Pega KM | KM - rollback procedure |  | High | Yes |  | Anjali | Completed
Pega KM | KM - SecOps (Checkmarx) |  | High | Yes |  | Kiran | Completed
Robotics Alerts in Aternity | Alerts |  | Medium/High |  | Yes | Harish
Robotics Alerts in Aternity | Dashboard |  | Medium/High |  | Yes | Harish
SC - 8.4 upgrade | SC 8.4 - e-mail Notification | Need to resolve issues before completing | Medium | Yes |  | Naveen | In Progress
SC - 8.4 upgrade | SC 8.4 - Non-PROD Pipeline |  | Medium | Yes |  | Naveen / Anjali | Completed
SC - 8.4 upgrade | SC 8.4 - Prod Pipeline |  | Medium | Yes |  | Naveen / Anjali | Testing
SC - 8.4 upgrade | SC 8.4 - rollback procedure |  | Medium | Yes |  | Naveen / Anjali | Completed
SC - 8.4 upgrade | SC 8.4 - SecOps (Checkmarx) |  | Medium | Yes |  | Prasanna | Completed
SC - 8.4 upgrade | SC 8.4 - SQL Automation |  | Medium | Yes |  | Kiran | In Progress
Splunk Migration from LH to ETO | Onboarding Data (AWS) |  | High | Yes | Yes | Hemant | Not Started
Splunk Migration from LH to ETO | Onboarding Data (Bamboo) |  | High | Yes | Yes | Hemant | Completed
Splunk Migration from LH to ETO | Onboarding Data (Jenkins) |  | High | Yes | Yes | Hemant | In Progress
Splunk Migration from LH to ETO | Onboarding Data (JIRA) |  | High | Yes | Yes | Hemant | Completed
Splunk Migration from LH to ETO | Onboarding Data (Open Shift) |  | High | Yes | Yes | Hemant | Testing
| Install Splunk and Onboard non-prod servers |  | High |  | Yes | Harish
ASPEN | Install Splunk and Onboard prod servers |  | High |  | Yes | Harish
ASPEN | Install AppD and onboard PERF servers |  | High |  | Yes | Harish
ASPEN | Install AppD and onboard PROD servers |  | High |  | Yes | Harish
Offshore Access | Access to Compass w/out PHI |  | High |  | Yes | Lakshmi
Dashboard Enhancements | Perf team needs enhancements to dashboards |  | Medium |  | Yes | Lakshmi
Deployment product details | SC Deployment product details Dashboard |  | Medium |  |  | Hemant | In progress
| Compass Deployment product details Dashboard |  | Medium |  |  | Hemant | Not Started
| SCC Deployment product details Dashboard |  | Medium |  |  | Hemant | Not Started
Pega Infra server details | SC Pega Infra server details |  | Medium |  |  | Hemant | Completed
| KM |  | Medium |  |  | Hemant | Completed
| Compass Pega Infra server details |  | Medium |  |  | Hemant | Not Started
DBG
| SCC Pega Infra server details |  | Medium |  |  | Hemant | In progress
Scripting automation | Manual vs Auto report |  | Medium |  |  | Hemant | In progress
SC pipeline logs | Onboard Splunk |  | High |  |  | Hemant | In progress
Checmarx API | Checmarx API to get test scores |  | High |  |  | Naveen
ASPEN | ASPEN - e-mail Notification |  | High |  |  | Kiran/Sri
ASPEN | ASPEN - Non-PROD Pipeline |  | High |  |  | Kiran/Sri
ASPEN | ASPEN - Prod Pipeline |  | High
ASPEN | ASPEN - rollback procedure |  | High |  |  | Sri
ASPEN | ASPEN - SecOps (Checkmarx) |  | High |  |  | Sri
ASPEN | APSEN - SQL automation |  | High |  |  | Kiran
Follow up
Tasks | Issue | POC | DevOps team
AWS SC sql automation | sql runner | Jaya or Vikram | Kiran
SC 8.4 - SQL Automation | prereq | Vikram or Srinivas
AWS SC rollback db issue |  | Vikram or Srinivas | Aishwarya
Jenkins integration with Splunk | Plugins | Vikram | Hemant
AWS UAT url |  | Vikram
Aws dpeloyment process | Merge
Compass DB migration sql automation |  |  | Prasanna
Compass prod pipeline | migration is going to happen 8.4.4
Follow up with in the team
Tasks | Issue | POC | DevOps team
KM testing pipeline scores in splunk |  | Hema | Hemant & Naveen
Pega app DB | Compass
MySQL
Oracle

## 2021 Acmp
DevOps before EagleEye
1. In Lighthouse Splunk Environment (had to pay for every enhancements)
2. Did not have any security scanning
3. Guardrail scores stop in dev env
4. No clear understanding why manual deployments were high
5. Pipelines needs to be streamlined
6. Limited to Smoke and Regression Testing
7. Rollback feature limited to Solution Central 731
8. No access to Infra Health
EagleEye DevSecOps
| 2. Implemented Checkmarx (application scanning) | Q1
| 3. Moved guardrail verification to PERF env (scan in lower env but does not stop) | Q3 |  | Application | CICD Pipelines |  | Roll back | Checkmarx | Cloudprisma | SQL automation | Testing pipeline Splunk integration |  | DevOps splunk
| 4. Reduced manual deployments and improved automated | Q4 |  |  | Non - Prod | Prod |  |  |  |  | Smoke | Regression
| Created a automated process to find the manual deployement |  | Q2, Q3 | SC | Completed | Completed | Pending | Completed | Completed | Completed | Pending | Pending | Completed
| a. Resolved pipeline issues in Compass |  |  | Compass |  |  |  | Completed | NA |  | Pending | Pending | Completed
| b. Removed guardrail blocker in dev env |  | Q2 | KM | Completed | Completed | Completed | Completed | NA | Completed | Completed | Pending | Completed
| c. Listen to user to get feedback on concerns and resolved | Q1 | Q3 | ASPEN - UPD | Completed | Completed | Pending | Completed | NA | Completed | Pending | Pending | Completed
| 5. Created a streamline pipeline that is easy to expand to any Pega environment |  | Q3 | DBG | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Pending | Completed
|  | Q2 |  | SCC |  | NA | NA | Completed | NA | NA | Completed | NA
| 7. Added the ability to rollback to previous code if something failed in deployments in SCC, KM, SC 8.4 |  | Q4 | DPDA | Completed | NA | Completed | Completed | NA | Completed | Manual | Manual
|  |  | Q2, Q3 | Chaos | Completed | NA | NA | NA | Completed | NA |  |  | Completed
| Completed Solution Central upgrade to 8.4 | Q3
Q3
| Implemented Prisma Cloud for docker image and container scanning | Q2
| Adoption rate automation | Q3
Sql automation for SC, KM, ASPEN, DBG, DPDA
uipath task
Enhancements
| Encryption |  | exp - comp
Pega
| Postdeployment check - compare it with previous env instead of Dev |  | exp - comp
| Adding application context for Guardrails on Product |  | exp - comp
| Cutomized logging |  | Vengat
Value added automations
Automated login process for Openshift
Support Other Project
1. AWS Migration
2. Solution Central upgrade to 8.4
3. Pega KM
4. ASPEN
5. Major / Minor Environments
6. Blue / Green Environments
7. Review UI Path to automate tasks in setting up CI/CD Pipelines

## Cloud & OnPrem
Pega Applications | Cloud (AWS OCP) | On-Premises
|  | OCP | Server
| SC Non-Prod | SC (PERF and PROD) | Compass
|  | DBG | KM
|  | SCC | ASPEN
| DevSecOps Tools | Cloud/On-Prem
|  | Current | Future
| JIRA | On-Prem
Bitbucket
Bamboo
Confluence
Artifactory
| Quay | AWS/On-Prem
| OCP, Jenkins | AWS/On-Prem
| PC | On-Prem
| Checkmarx | Anthem AWS | Vendor
| Prisma cloud | Vendor
| Splunk | On-Prem

## Peag apps
Application | CI/CD Pipeline | Splunk | Aternity | AppDynamics | Best Practices
Anthem Single Provider Experience Network (ASPEN) | Yes | Yes | Yes | Yes | Yes
CCP-DBG Solution Central | Yes | Yes | Yes | Yes | Yes
CCP-Solution_Central | Yes | Yes | Yes | Yes | Yes
Compass (GBD) | Yes | Yes | Yes | Yes | Yes
Pega Knowledge Management | Yes | Yes | Yes | Yes | Yes
Sydney Care Central | Yes | Yes | Yes | Yes | Yes
ACMS UM Intake (AUMI) | In Progress | Yes | Yes | PERF
Anthem Experience PEGA Platform
CCP-CPSUI |  | Yes | Yes |  | Yes
CCP-ePortal_HelpDesk
CCP-EVP (Enterprise Voice Portal) |  | Yes | Yes
CCP-MCC_C
CCP-Verint
Collateral Update Engine
ECHO - VOICE OF CUSTOMER PEGA APP
GBD Pharmacy Prior Authorization Review Tool (PAR ) (IRx)
LiveEngage - Agent Health Trigger Widget
NextGen Pega Grievance & Appeals (GBD/FEP/Commercial) | In Progress | Yes |  | PERF
Pega Customer Decision Hub |  | Yes
PEGA Utility for Managing Access (PUMA)
Pega Workforce Intelligence
Personal Information Privacy Rights System (PIPRS)
Predictive Modeling Drilldown Tool (Enterprise)
Provider Engagement Platform (PEP) |  | Yes
SPS | In Progress

## EE_DO
Tools/Technologies |  |  |  | Architecture | Clearcase | AWS
|  |  |  | Infra Setup | BuildForge | Azure/Azure DevOps
SCM | Git |  | Pega | Networking | XLDeploy | Ansible
| Bitbucket |  | Java |  | SonarQube | Terraform
[5 empty] | AgileCraft | LogicMonitor
CICD | Bamboo |  |  |  | MS Build
| Jenkins |  |  |  |  | Helm
| Udeploy |  |  |  |  | GitLab CI
Security | Prisma Cloud |  |  |  |  | Nexus
Snyk
Checkmarx
Repository | Artifactory
Quay
Dockerization | Docker
Kubernetes/OCP
Maven
Web Servers | Websphere
Liberty
Scripting | Shell
Powershell
IVR Testing | Cyara
RPA | UiPath
Monitoring | Splunk
AppD
Aternity/NexThink
ThousandEyes
| DataDog | OCP support
Tableau
POC | DataDog | Vs AppD
| Performance Center | Splunk Integration
| Liquibase | SQL automation
| Argo CD | OCP automation
| Python | Scripting
Tracking & Documentation | Jira
Confluence
Snow

## KT
S.No | KT Topic | Introduction | Complete KT | Practice Time | Demo/Reverse KT | POC 1 | POC 2
1 | DevOps | Completed | Completed | Completed | Completed | Naveen | Aishwarya
2 | Bitbucket/Git | Completed | Completed | Completed | Completed | Aishwarya | Kiran
3 | Bamboo | Completed | Completed | Completed | Completed | Srinaveen | Kiran
4 | Jenkins | Completed | Completed | completed |  | Kiran | Prasanna
5 | Artifactory | Completed | Completed | completed |  | Aishwarya | Prsanna
6 | Jira | Completed | Completed | completed |  | Srinaveen | Aishwarya
7 | Confluence | Completed | Completed | completed |  | Srinaveen | Aishwarya
8 | Linux/Shell scripts | Completed | Completed | completed |  | Srinaveen | Kiran
9 | Docker | Completed | Completed | completed |  | Kiran | Prasanna
10 | OCP | completed | Completed |  |  | Prasanna | Srinaveen
Beginner Knowledge
1 | Splunk | Completed | Completed |  |  | Vengat | Saketha
2 | Pega | Completed | Completed |  |  | Naren | Ruby
3 | Quay | Completed | Completed |  |  | Prasanna | Kiran
4 | Checkmarx | Completed | Completed |  |  | Aishwarya | Prasanna
5 | Prisma Cloud | Completed | Completed |  |  | Aishwarya | Prasanna
6 | Performance Center | Completed | Completed |  |  | Srinaveen | Aishwarya
7 | Agile method | Completed | Completed |  |  | Prasanna | Naveen
8 | SNOW | Completed | Completed |  |  | Prasanna | Srinaveen
Project DevOps KT
1 | SC |  |  |  |  | Kiran | Aishwarya
2 | Compass | [5 empty] | Ruby
3 | ASPEN |  |  |  |  | Srinaveen | Prasanna
4 | KM | Completed | Completed |  |  | Kiran | Naren
5 | DBG |  |  |  |  | Aishwarya | Kiran
6 | SCC |  |  |  |  | Prasanna | Naveen
7 | DPDA |  |  |  |  | Aishwarya | Prasanna
8 | Chaos applications |  |  |  |  | Prasanna | Srinaveen
Pega APIs and Testing
DevOps setup for a new project
DevOps pipeline testing
Perf testing
Prod pipeline setup
PROD region deployment
PROD region validation
Daily tasks
Application quality check
Common issues during pipeline setup
Common issues post pipeline setup

## Sheet2
ASPEN | Add Enhancements to ASPEN Report in Tableau
ASPEN | Monitoring: Eagle eye requirements for monitoring health for DDC in Aspen
EE Automation | Migrate User ID Report into Tableau
EE Automation | SPlunk Api Health Report
EE Automation | UI Path: Connectivity Check from Bamboo Agent to Jira, UCD, Sonar, Bitbucket, Bamboo
EE Automation | UI Path: Performance center integration with Splunk
EE Automation | UiPath: EagleEye API Health Daily Report
EE Maintenance | Add 1 or 2 Heavy Forwarder Splunk Server
EE New Tools | Evaluate Argo CD for OpenShift configuration
NexGen | DevOps (CI/CD Pipeline) - NonProd
NexGen | Monitoring Tools (AppD) - non-prod & prod
NexGen | Monitoring Tools (Splunk)
NexGen | Security
NexGen | SMART DevOps Dashboards, Testing Report Dashboards
Support Others | Pega Robotics: Customer Dashboard to showcase ASPEN
Support Others | SC: Balance & Control
Voice Service | Checkmarx integration (Security)
Voice Service | Cyara integration (Testing)
Voice Service | DevOps (CI/CD Pipeline)
Voice Service | Snyk integration (Security)
Voice Service | Splunk integrated Dashboard
ASPEN | Customer Dashboard to showcase NextGen
AUMI | Monitoring Tools (AppD & NexThink)
AUMI | Monitoring Tools (Splunk)
AUMI | Pega Code Changes
AUMI | Pega Code Changes - Dual DevOps APP
AUMI | Security
EagleEye | Add Broadcom data in Integrated Dashboard
EagleEye | Add Database Monitoring in Splunk
EagleEye | Add DataDog into EagleEye suite
EagleEye | Add OpenShift Infrastructure monitoring (DataDog) – 13th May
EagleEye | Maintain EagleEye Documentation for all the modules/Data sources for Splunk work
EagleEye | Renew AppDynamics license and expand to all Pega apps – Sai
EE Automation | Tableau:Enhancements to the User Report
EE Automation | Tableau: Add ASPEN & Pega KM to User Report
EE Automation | UI Path: Bamboo agent configuration
EE Automation | UI Path: CICD pipeline configuration
EE Automation | UI Path: Setup and Test Pega DevOps API’s
EE Automation | UI Path: Services and routes configuration for Chaos applications
EE Automation | UI Path: Splunk: HTML dashboard report automation
EE Enhancements | Allow deployments from QA Environments
EE Enhancements | Deployment summay dashboard - Jira ticket integration using Python
EE Enhancements | GBD Compass: Balance & Controls
EE Enhancements | Handling multiple environments deployment from the same pipeline
EE Enhancements | Improvement on deployment trigger
EE Enhancements | Notification to developer based on pega ruleset lock.
EE Enhancements | Post deployment and Release note file in CSV format instead of exisiting xlsx/xls file
EE Enhancements | Smoke and Regression data integration and Dashboard
EE Maintenance | Enhance/clean-up EagleEye Splunk Dashboards to utilize indexed time extractions
EE Maintenance | Pega security checklist
EE New Tools | AppD vs DataDog evaluation
EE New Tools | MS SQL automation
EE New Tools | Expand Thousandeyes
EE New Tools | Implementing Argocd for SC, DBG and Chaos applications
EE New Tools | Prisma cloud data integration & Dashboard
EE New Tools | Rollout NexThink and migrate from Aternity
EE UX | EagleEye dashboard redesign (Confidence in defect free deployments)
EE UX | EagleEye dashboard redesign (Health Scores)
EE UX | EagleEye dashboard redesign (Manager View (summary of all apps))
EE UX | One-page Splunk for each application (Deployment summary)
Fusion | DevOps (CI/CD Pipeline)
EE Enhancements | Solution Central: Come up with API alerting thresholds
EE Enhancements | Solution Central: Create a new dashboard to track critical Pega Errorcode Metrics trends for CSRID
EE Enhancements | Solution Central: Create new alerts for PEGA0019, PEGA0086, PEGA0026, ThreadDumps, DBConnectivity, SQL Transient & Hazelcast scenarios.
Fusion | Monitoring Tools
GBD Compass | Enable boot start for all linux & Windows prod & non-prod servers
Fusion | Monitoring Tools (Splunk)
Fusion | Pega Code Changes
Fusion | Security
NexGen | DevOps (CI/CD Pipeline) - Prod
One Portal | DevOps (CI/CD Pipeline)
One Portal | Monitoring Tools (AppD & NexThink)
One Portal | Monitoring Tools (Splunk)
One Portal | Pega Code Changes
One Portal | Security
PPMS | DevOps (CI/CD Pipeline)
PPMS | Pega Code Changes
Smart Intake | Monitoring Tools (AppD & NexThink)
Smart Intake | DevOps (CI/CD Pipeline)
Smart Intake | Monitoring Tools (Splunk)
Smart Intake | Pega Code Changes
Smart Intake | Security
SPS | Guardrail monitoring
SPS | Monitoring Tools (AppD & NexThink)
SPS | Monitoring Tools (Splunk)
Voice Service | New applications on boarding
Voice Service | Monitoring Tools (AppD & NexThink)
Voice Service | Monitoring Tools (Splunk) - Genesys
Voice Service | Monitoring Tools (Splunk) - IVR